## ✅ Completed Tasks
# | Module | Feature / Task | Source Document | Status
Doctor Account (25 items)
1 | Doctor Account | Sidebar: Rename 'NAVIGATION' → 'MY ACCOUNT' | 12 April | ✅ Done
2 | Doctor Account | Sidebar: Remove Heart Icon, View Lab Reports, iCare text, PRO badge | 12 April | ✅ Done
3 | Doctor Account | Sidebar: Remove Logout button from bottom | 12 April | ✅ Done
4 | Doctor Account | Sidebar: Remove Doctor Name + Image from header | 12 April | ✅ Done
5 | Doctor Account | Sidebar: Remove 'QUICK ACTIONS' section label | 12 April | ✅ Done
6 | Doctor Account | Logout moved to profile dropdown (Edit Profile + Logout) | 12 April | ✅ Done
7 | Doctor Account | Dashboard: Rename 'Clinical Audit' → 'Quality Score' | 12 April | ✅ Done
8 | Doctor Account | Dashboard: Remove 'Care Programs' card | 12 April | ✅ Done
9 | Doctor Account | Credential Vault renamed to 'Certificate' with new icon | 12 April | ✅ Done
10 | Doctor Account | Help Center: Phone number updated to +923068961564 | 12 April | ✅ Done
11 | Doctor Account | Settings: Remove 'Danger Zone' / Delete Account section | 12 April | ✅ Done
12 | Doctor Account | Settings: Remove 'Subscription Plan' item | 12 April | ✅ Done
13 | Doctor Account | Dashboard layout order: Welcome → Appointment Requests → Today's Appts → Consultations count | 13 April | ✅ Done
14 | Doctor Account | Dashboard: Revenue section removed from home page | 13 April | ✅ Done
15 | Doctor Account | Appointment Requests widget: Accept/Decline buttons, 5 at a time with View All | 13 April | ✅ Done
16 | Doctor Account | Today's Appointments: square cards by time, Total Patients Today, View All link | 13 April | ✅ Done
17 | Doctor Account | Pending Appointments count replaces Revenue card | 13 April | ✅ Done
18 | Doctor Account | Revenue & Analytics section added (consistent across all accounts) | 18 April | ✅ Done
19 | Doctor Account | Recent Activity widget on dashboard | 18 April | ✅ Done
20 | Doctor Account | My Profile moved to top-right icon (removed from sidebar) | 18 April | ✅ Done
21 | Doctor Account | Consultation settings: Online/Offline toggle, Instant Consultation toggle | 4 May | ✅ Done
22 | Doctor Account | Patient history access during consultation; loses access after | 4 May | ✅ Done
23 | Doctor Account | Rename 'Patient History' → 'Past Consultations' | 4 May | ✅ Done
24 | Doctor Account | Pending requests: 3-minute waiting time notification with patient details | 4 May | ✅ Done
25 | Doctor Account | Appointment management: upcoming, completed, rejected | 4 May | ✅ Done
Patient Account (13 items)
26 | Patient Account | Book a Lab Test — multi-step flow (Sample Type, Select Tests, Nearby Labs) | 13 April | ✅ Done
27 | Patient Account | Order Medicines: search bar, ecommerce list, medicine details popup, quantity option | 13 April | ✅ Done
28 | Patient Account | Settings: Remove Privacy Policy, About Us, Terms and Conditions | 13 April | ✅ Done
29 | Patient Account | SOAP Notes hidden from patient view (doctor-facing only) | 13 April | ✅ Done
30 | Patient Account | Emergency Contact fields (2 fields) added to patient profile | 13 April | ✅ Done
31 | Patient Account | Patient profile: add CNIC, remove role field | 13 April | ✅ Done
32 | Patient Account | Booking History redesign: card layout, pending at top | 13 April | ✅ Done
33 | Patient Account | Patient sidebar renames: Order Medicines, Book a Lab Test, My Appointments at top | 13 April | ✅ Done
34 | Patient Account | Contact privacy: patient contact info not visible to doctors | 14 May | ✅ Done
35 | Patient Account | My Prescriptions: latest (30 days) with order buttons; older = view-only | 4 May | ✅ Done
36 | Patient Account | My Lab Tests & My Medicines order history/status sections | 4 May | ✅ Done
37 | Patient Account | Consultation: For Myself / For Someone Else options | 4 May | ✅ Done
38 | Patient Account | Reason for consultation: changed from mandatory to optional | 4 May | ✅ Done
Home Page (27 items)
39 | Home Page | Public home redesigned (OlaDoc style); 3 navbar buttons: Sign In, Sign Up, Work With Us | 11 April | ✅ Done
40 | Home Page | Post-login: right-side panel removed | 11 April | ✅ Done
41 | Home Page | Left nav drawer: removed profile photo, name, email; iCare logo at top; renamed to 'My Account' | 11 April | ✅ Done
42 | Home Page | Profile appears only in top-right corner (no duplication) | 11 April | ✅ Done
43 | Home Page | Search bar: 3 modes — Doctor Name, Speciality, Condition | 13 April | ✅ Done
44 | Home Page | 'Connect Now' button added (goes to available/online doctors) | 13 April | ✅ Done
45 | Home Page | Courses section: 'Join Pakistan's First 360° Health Care Platform', 2x2 grid tiles | 13 April | ✅ Done
46 | Home Page | Separate search bars for Doctors, Pharmacy, Labs | 13 April | ✅ Done
47 | Home Page | WhatsApp floating action button (bottom-right, always visible) | 13 April | ✅ Done
48 | Home Page | Pharmacy and Lab star ratings on listing pages | 13 April | ✅ Done
49 | Home Page | Logo reverted to original (iCare text at bottom), center-aligned | 18 April | ✅ Done
50 | Home Page | All three section headings (Doctors/Pharmacy/Labs) fully clickable | 18 April | ✅ Done
51 | Home Page | 'Consult Available Doctors' → 'Connect to a Doctor Now' | 18 April | ✅ Done
52 | Home Page | Online doctors shown on home page; search bar placed as per client | 18 April | ✅ Done
53 | Home Page | Browse by Specialty + Browse by Condition restored below doctor cards | 18 April | ✅ Done
54 | Home Page | App Store / Play Store buttons non-clickable until app is live | 18 April | ✅ Done
55 | Home Page | LMS block: non-clickable / Coming Soon; 3 options: For Patient, For Professionals, Explore All | 18 April | ✅ Done
56 | Home Page | Banner heading → 'Consult a Doctor'; sub-text updated | 21 April | ✅ Done
57 | Home Page | Banner: iCare logo as faded watermark; doctor image in front; logo badge on doctor coat | 21 April | ✅ Done
58 | Home Page | Navbar logo fixed: cropped, slightly larger, navbar height +20% | 21 April | ✅ Done
59 | Home Page | Doctor section heading → 'Consult Available Doctors Now' | 21 April | ✅ Done
60 | Home Page | 'Order Medicines' heading color → Shopify green | 21 April | ✅ Done
61 | Home Page | 'Book a Lab Test' heading color → #FF4D00; button pulsing animation + bold text | 21 April | ✅ Done
62 | Home Page | LMS section: reduced from 4 tiles to 2 tiles | 21 April | ✅ Done
63 | Home Page | 'How iCare Works': updated to 5 steps with two-path branching arrows | 21 April | ✅ Done
64 | Home Page | Footer: updated description text, App Store buttons black, logo fixed | 21 April | ✅ Done
65 | Home Page | Login screen: feature boxes updated (HIPAA, Data Protected, colorful icons); logo area: logos only | 21 April | ✅ Done
Video Consultation (5 items)
66 | Video Consultation | Chat-first consultation flow (video does not start automatically) | 4 May | ✅ Done
67 | Video Consultation | Chat screen: doctor name, patient name, chat box, attachment, send, voice/video call, timer, End button | 4 May | ✅ Done
68 | Video Consultation | Automatic consent message sent at chat start | 4 May | ✅ Done
69 | Video Consultation | Leave Video (red) + End Consultation (purple) buttons with popups | 4 May | ✅ Done
70 | Video Consultation | Minimum 15 min / Maximum 30 min consultation duration with timer | 4 May | ✅ Done
Prescription Management (6 items)
71 | Prescription Management | Prescription button within video/chat interface; form fills during consultation | 4 May | ✅ Done
72 | Prescription Management | Prescription form: Patient History, SOAP Notes, Doctor Notes, Diagnosis (ICD-10), Medications, Lab Tests, Referral & Follow-up, Course Assignment | 4 May | ✅ Done
73 | Prescription Management | Cannot end consultation without completing prescription (error popup) | 4 May | ✅ Done
74 | Prescription Management | Prescription auto-publishes to patient when consultation ends | 4 May | ✅ Done
75 | Prescription Management | Prescription PDF: patient info, doctor info, diagnosis, medications, lab tests, doctor notes, order buttons | 4 May | ✅ Done
76 | Prescription Management | ICD-10 codes integrated; medicine database (British Pharmacopoeia); standard lab catalogue | 4 May | ✅ Done
Health Tracker (13 items)
77 | Health Tracker | Main dashboard: greeting, daily goal progress bar, points earned, metric tiles | 13 April | ✅ Done
78 | Health Tracker | Vitals tracking: BP, Blood Sugar, Weight, Heart Rate, SpO2 | 13 April | ✅ Done
79 | Health Tracker | Lifestyle tracking: Water intake, Steps, Sleep, Diet/Meals | 13 April | ✅ Done
80 | Health Tracker | Medication & Compliance: taken toggle, reminders, missed dose, prescription link | 13 April | ✅ Done
81 | Health Tracker | Mental health: Mood tracking, Stress level, Menstrual cycle, Hydration reminders, Calories | 13 April | ✅ Done
82 | Health Tracker | Metric logging with input fields, numeric keypad, Save, +points message | 13 April | ✅ Done
83 | Health Tracker | Progress Charts: Daily/Weekly/Monthly tabs, line charts, achievement badges | 13 April | ✅ Done
84 | Health Tracker | Health Mode toggle: Diabetes / BP / General Wellness / Custom | 13 April | ✅ Done
85 | Health Tracker | Gamification: log metric = +5pts, daily goal bonus, streak bonus | 13 April | ✅ Done
86 | Health Tracker | Rewards screen: points balance, activity feed, Redeem Points button | 13 April | ✅ Done
87 | Health Tracker | Redeem screen: Free Consultation (100 pts), Lab Test Discount (150 pts), redemption charts | 13 April | ✅ Done
88 | Health Tracker | Tracker settings: ON/OFF toggles for each metric; daily goals (water, steps) | 13 April | ✅ Done
89 | Health Tracker | Health Journey: filtered view based on selected health conditions | 4 May | ✅ Done
Pharmacy Account (27 items)
90 | Pharmacy Account | Dashboard stats order: Today, Total, Pending, Completed | 18 April | ✅ Done
91 | Pharmacy Account | Revenue & Analytics: total orders, acceptance, completion, response time, ratings, complaints, etc. | 18 April | ✅ Done
92 | Pharmacy Account | Recent Activity widget on dashboard | 18 April | ✅ Done
93 | Pharmacy Account | Sidebar final order: Dashboard, Awaiting Fulfillment, Orders, Inventory, Invoices, Revenue & Analytics, Settings, Support Chat | 18 April | ✅ Done
94 | Pharmacy Account | Orders management: Prescriptions renamed Orders; Create Order button added | 18 April | ✅ Done
95 | Pharmacy Account | My Profile removed from sidebar → moved to top-right icon | 18 April | ✅ Done
96 | Pharmacy Account | Order lifecycle: Accept → Prepare → Dispatch (mandatory delivery time) → Delivered → Rating prompt | 18 April | ✅ Done
97 | Pharmacy Account | Order detail fields: patient name, phone, address, email, items, prescription, delivery fee, total | 18 April | ✅ Done
98 | Pharmacy Account | Pharmacist marks delivery (customer cannot confirm — fraud prevention) | 18 April | ✅ Done
99 | Pharmacy Account | Printable PDF invoice with iCare branding; PKR currency | 18 April | ✅ Done
100 | Pharmacy Account | Controlled medicines: consultation required flow; 30-unit cap without prescription | 18 April | ✅ Done
101 | Pharmacy Account | Doctor prescription: prescribed quantity passes directly, no system limit | 18 April | ✅ Done
102 | Pharmacy Account | Vaccines: require prior consultation | 18 April | ✅ Done
103 | Pharmacy Account | Delivery fee: set by pharmacy per branch; included in checkout total | 18 April | ✅ Done
104 | Pharmacy Account | Inventory bulk upload/download via Excel/CSV template | 18 April | ✅ Done
105 | Pharmacy Account | Inventory fields: brand name, generic name, category, price PKR, stock qty, unit | 18 April | ✅ Done
106 | Pharmacy Account | Pharmacist-initiated manual order; controlled drug requires iCare prescription | 18 April | ✅ Done
107 | Pharmacy Account | Rating system: star (1-5) + comment; visible on profile; sent after order completion | 18 April | ✅ Done
108 | Pharmacy Account | Notifications: Order dispatched, delivery updates, system alerts; remove booking updates | 18 April | ✅ Done
109 | Pharmacy Account | Pharmacy profile fields: name, drug sale license, address, contact, hours, DRAP checkbox | 18 April | ✅ Done
110 | Pharmacy Account | Change Password flow: old → new → confirm | 18 April | ✅ Done
111 | Pharmacy Account | Settings: removed patient-facing items (health profile, consultation, test history, LMS, booking updates) | 18 April | ✅ Done
112 | Pharmacy Account | Support: Report an Issue form → sent to iCare admin email | 18 April | ✅ Done
113 | Pharmacy Account | iCare Pharmacist Support: direct chat with iCare team (WhatsApp-style) | 18 April | ✅ Done
114 | Pharmacy Account | Onboarding (Work With Us): 3-step form for Doctor, Pharmacy, Lab with DRAP compliance | 18 April | ✅ Done
115 | Pharmacy Account | Patient Name label added above patient name in order detail | 21 April | ✅ Done
116 | Pharmacy Account | All $ signs replaced with PKR/Rs | 21 April | ✅ Done
Laboratory Account (30 items)
117 | Laboratory Account | Dashboard stats: Today, Total, Pending, Completed | 18 April | ✅ Done
118 | Laboratory Account | Sidebar: Dashboard, New Requests, Orders, Test Catalog, Result Entry, Invoices, Revenue & Analytics, Support Chat | 18 April | ✅ Done
119 | Laboratory Account | Test Catalog: standardized names, price PKR, turnaround time, sample type, search bar | 18 April | ✅ Done
120 | Laboratory Account | Standardized test nomenclature across Doctor/Patient/Lab interfaces | 18 April | ✅ Done
121 | Laboratory Account | Lab-initiated walk-in order creation | 18 April | ✅ Done
122 | Laboratory Account | Result Entry + Upload Reports merged into one page | 18 April | ✅ Done
123 | Laboratory Account | Invoices: PKR, iCare branding, downloadable PDF | 18 April | ✅ Done
124 | Laboratory Account | Revenue & Analytics: earnings PKR, payout history, volume, acceptance/completion rate, ratings, invoices | 18 April | ✅ Done
125 | Laboratory Account | Lab public profile shows test catalog to patients/doctors | 18 April | ✅ Done
126 | Laboratory Account | Lab profile fields: name, license, address, contact, hours, DRAP agreement | 18 April | ✅ Done
127 | Laboratory Account | Notification preferences: new test requests, sample collection updates, result reminders, system alerts | 18 April | ✅ Done
128 | Laboratory Account | Lab settings scoped to lab-relevant options only | 18 April | ✅ Done
129 | Laboratory Account | Help/Support: lab-specific FAQ; Report an Issue → admin email | 18 April | ✅ Done
130 | Laboratory Account | Sidebar updated: removed Awaiting Fulfillment, Result Entry; renamed Upload Reports → Records | 21 April | ✅ Done
131 | Laboratory Account | Lab order status flow: New Request → Accepted → Sample Collected → Awaiting Reports → Reporting Done → Cancelled | 21 April | ✅ Done
132 | Laboratory Account | New Requests sorted by date (oldest first); filter options added | 21 April | ✅ Done
133 | Laboratory Account | Word 'Appointment' removed from all lab order flows | 21 April | ✅ Done
134 | Laboratory Account | Sample Collected button accessible from main order list | 21 April | ✅ Done
135 | Laboratory Account | Lab booking detail view: Lab Name, Ordered By, Patient Name, Prescription Date, Referred By, Collection Type, Doctor Notes, Sample Collected By | 21 April | ✅ Done
136 | Laboratory Account | Walk-in order form: Patient Name, Age, Gender, Location, MR Number, Prescription Date, Referred By, Specimen ID (multi-row), Collection Type, Urgency toggle, PKR pricing | 21 April | ✅ Done
137 | Laboratory Account | Test Catalog Add form: standardized dropdown, PKR, Sample Collection Type, turnaround time, urgent option | 21 April | ✅ Done
138 | Laboratory Account | Result entry flow: Sample Collected → Enter Results → Approved by Doctor dropdown → Reporting Done | 21 April | ✅ Done
139 | Laboratory Account | Result Entry: test parameters with values/units/reference ranges, Sample Collected By dropdown, Doctor's Notes, Upload PDF | 21 April | ✅ Done
140 | Laboratory Account | Revenue: two fields (Card vs Cash); calculation breakdown; date range picker; ratings/reviews | 21 April | ✅ Done
141 | Laboratory Account | Invoices: only confirmed/completed records shown (removed pending/overdue) | 21 April | ✅ Done
142 | Laboratory Account | Lab profile setup: name, owner, license, multiple contact numbers, email, working hours, home collection toggle, logo upload, document uploads, DRAP checkbox | 21 April | ✅ Done
143 | Laboratory Account | Doctors Panel in lab profile: up to 6 doctors, name + education + designation; appear on reports | 21 April | ✅ Done
144 | Laboratory Account | Sample Collectors Panel: name + designation; linked to sample collection entries | 21 April | ✅ Done
145 | Laboratory Account | Lab notifications: remove Booking Cancellation, Payment Received, Low Supply Alert, Daily Summary | 21 April | ✅ Done
146 | Laboratory Account | iCare Lab Support: WhatsApp button in Help Center | 21 April | ✅ Done
LMS (7 items)
147 | LMS | LMS ~60% complete (was 20%) | 4 May | ✅ Done
148 | LMS | Course browsing without login | 4 May | ✅ Done
149 | LMS | Learning Dashboard, My Courses, Assignments (upload/submit), Quizzes/Assessments, Live Sessions, Course Progress Tracking | 4 May | ✅ Done
150 | LMS | Instructor: Course Creation, Content Upload, Quiz/Assignment Creation, Student Progress Monitoring, Live Session Scheduling | 4 May | ✅ Done
151 | LMS | Admin: Student Verification, Course Approval, Instructor Management, Analytics Dashboard | 4 May | ✅ Done
152 | LMS | 'My Learning' button in all user dashboards | 4 May | ✅ Done
153 | LMS | Instructor portal accessible only to approved doctors | 4 May | ✅ Done
Registration / Sign-up (9 items)
154 | Registration / Sign-up | Single sign-in for all roles: Email/Password, Google Sign-in | 4 May | ✅ Done
155 | Registration / Sign-up | Patient Sign-up: simple form (Name, Email, Phone, Password, T&C) | 4 May | ✅ Done
156 | Registration / Sign-up | Professional registration: Doctor, Pharmacy, Lab, Instructor, Student role selection | 4 May | ✅ Done
157 | Registration / Sign-up | Doctor registration: qualification, PMDC, experience, availability, document upload (CNIC, degree, CV) | 4 May | ✅ Done
158 | Registration / Sign-up | Pharmacy registration: business name, drug license, years, location, contact, documents, T&C | 4 May | ✅ Done
159 | Registration / Sign-up | Lab registration: name, license, location, contact, LIS details, documents, T&C | 4 May | ✅ Done
160 | Registration / Sign-up | Student registration: minimal form (Name, Email, Phone, Password; institute/degree optional) | 4 May | ✅ Done
161 | Registration / Sign-up | Role approval logic: Patient/Student auto-approved; Doctor/Pharmacy/Lab needs admin approval | 4 May | ✅ Done
162 | Registration / Sign-up | Login screen: tagline 'Your Trusted Healthcare Platform', 'iCare by RM Health Solution', RM Health Solutions logo | 18 April | ✅ Done
General / Cross-cutting (15 items)
163 | General / Cross-cutting | Star rating (1-5) + comment visible on doctor, pharmacy, lab profiles | 18 April | ✅ Done
164 | General / Cross-cutting | Rating prompt sent immediately after each completed service | 18 April | ✅ Done
165 | General / Cross-cutting | All invoices/financial displays use PKR | 18 April | ✅ Done
166 | General / Cross-cutting | Recent Activity widget on all service-provider dashboards | 18 April | ✅ Done
167 | General / Cross-cutting | Separate onboarding forms for Doctor, Pharmacy, Lab via Work With Us | 18 April | ✅ Done
168 | General / Cross-cutting | Account-specific Help Center content (no cross-account bleed) | 18 April | ✅ Done
169 | General / Cross-cutting | Account-specific settings pages | 18 April | ✅ Done
170 | General / Cross-cutting | All PDFs: iCare branding prominent; provider name secondary; PKR currency | 18 April | ✅ Done
171 | General / Cross-cutting | Multi-language support: English + Urdu; language toggle in settings | 4 May | ✅ Done
172 | General / Cross-cutting | Biometric login (device-level) | 4 May | ✅ Done
173 | General / Cross-cutting | HIPAA compliance considerations | 4 May | ✅ Done
174 | General / Cross-cutting | Doctor: instant consultation request notifications (3-min window); Patient: accept/reject notifications | 4 May | ✅ Done
175 | General / Cross-cutting | Health Community: like and comment feature | 13 April | ✅ Done
176 | General / Cross-cutting | Notification settings cleanup | 13 April | ✅ Done
177 | General / Cross-cutting | Language & Region settings | 13 April | ✅ Done
Newly Added Completed (2 items)
178 | Doctor Account | Doctor Signup page: Hours selection UI improved | New | ✅ Done
179 | Registration / Sign-up | Valid Email and Valid Phone Number validation on submission | New | ✅ Done

## ⏳ Pending Tasks
# | Module | Feature / Task | Source Document | Priority | Status
Doctor Account (8 items)
1 | Doctor Account | Clinical Flags: abnormal activity flags in analytics panel | 14 May | High | ⏳ Pending
2 | Doctor Account | Revenue & Analytics: improved filters and content | 14 May | High | ⏳ Pending
3 | Doctor Account | My Appointments: missed appointments category with limited patient info | 14 May | High | ⏳ Pending
4 | Doctor Account | My Schedule (Calendar): visual and stats improvements | 14 May | Medium | ⏳ Pending
5 | Doctor Account | Certificates: doctor uploads → admin verifies | 14 May | Medium | ⏳ Pending
6 | Doctor Account | Availability/Unavailability management: doctor requests leave → admin approves | 14 May | Medium | ⏳ Pending
7 | Doctor Account | Professional Settings Panel: restructure doctor's professional settings page | 14 May | Medium | ⏳ Pending
8 | Doctor Account | Doctor Profile: spoken languages field + searchable in doctor listing | 14 May | Medium | ⏳ Pending
Patient Account (8 items)
9 | Patient Account | My Health Journey: 'Coming Soon' banner | 13 April | Medium | ⏳ Pending
10 | Patient Account | My Health Journey: doctor prescription auto-appears; chronological order | 13 April | Medium | ⏳ Pending
11 | Patient Account | Family Profiles (linked accounts) — emergency contacts added as alternative | 13 April | Low | ⏳ Pending
12 | Patient Account | Patient settings: Phone & Email with verification badges; Address field | 4 May | Medium | ⏳ Pending
13 | Patient Account | Student: auto-approved after payment (for courses) | 4 May | Medium | ⏳ Pending
14 | Patient Account | Help Center: replace direct number with UAN; remove WhatsApp for patients | 14 May | Medium | ⏳ Pending
15 | Patient Account | Settings: language and region restrictions for patients | 14 May | Medium | ⏳ Pending
16 | Patient Account | Notification settings: simplify patient notification options | 14 May | Medium | ⏳ Pending
Video Consultation (1 items)
17 | Video Consultation | Consultation Summary card before connecting (tracker data + doctor notes + Start button) — Not needed (2 consultation paths exist) | 13 April | Low | ⏳ Pending
Pharmacy Account (6 items)
18 | Pharmacy Account | Third-party delivery API integration (Bykea, InDrive, Careem) — out of scope current phase | 18 April | Low | ⏳ Pending
19 | Pharmacy Account | GPS live delivery tracking — out of scope (replaced by expected delivery time) | 18 April | Low | ⏳ Pending
20 | Pharmacy Account | Bank/Account details not editable in-app; manual update via head office | 18 April | Low | ⏳ Pending
21 | Pharmacy Account | New Orders notification: mandatory, cannot be turned off | 18 April | High | ⏳ Pending
22 | Pharmacy Account | E-Mareez compatibility: align import template with E-Mareez export format | 18 April | Medium | ⏳ Pending
23 | Pharmacy Account | 'Ordered by Doctor' → 'Ordered by' (remove duplicate 'Doctor' word) | 21 April | Low | ⏳ Pending
Laboratory Account (11 items)
24 | Laboratory Account | Lab Recent Activity widget on dashboard | 18 April | Medium | ⏳ Pending
25 | Laboratory Account | Lab Settings page completion | 18 April | High | ⏳ Pending
26 | Laboratory Account | Result delivery to patient (in-app notification) and referring doctor after results ready | 18 April | High | ⏳ Pending
27 | Laboratory Account | API Integration with major lab chains (Chughtai, Agha Khan, etc.) — each requires separate integration | 18 April | Low | ⏳ Pending
28 | Laboratory Account | Payment gateway: all payments through iCare; payouts managed via admin portal | 18 April | High | ⏳ Pending
29 | Laboratory Account | Records page search: by Patient Name, MR Number, Doctor Name, Contact Number | 21 April | High | ⏳ Pending
30 | Laboratory Account | Report PDF footer: 'Electronically generated report verified by [Doctor Name]' | 21 April | Medium | ⏳ Pending
31 | Laboratory Account | Report PDF: all registered doctors' names at bottom; Sample Collected By shown | 21 April | Medium | ⏳ Pending
32 | Laboratory Account | Lab notifications: New Booking Alert + Urgent Test Alert (mandatory, cannot be disabled) | 21 April | High | ⏳ Pending
33 | Laboratory Account | Lab profile: Email OTP verification + Phone SMS OTP verification | 21 April | High | ⏳ Pending
34 | Laboratory Account | Platform fee feature — client requested to DELETE this feature | 21 April | High | ⏳ Pending
LMS (17 items)
35 | LMS | Course purchase flow: Buy Now → Sign-up → Payment → Limited access → Doc verification → Full access after admin approval | 4 May | High | ⏳ Pending
36 | LMS | Grades system for students | 4 May | High | ⏳ Pending
37 | LMS | Attendance tracking | 4 May | Medium | ⏳ Pending
38 | LMS | Grading system for instructors | 4 May | High | ⏳ Pending
39 | LMS | Feedback system | 4 May | Medium | ⏳ Pending
40 | LMS | Payment Management for admin | 4 May | High | ⏳ Pending
41 | LMS | 'Telehealth' button in student dashboard linking to patient services | 4 May | Medium | ⏳ Pending
42 | LMS | Instructor: separate email NOT required (can switch role) | 4 May | Medium | ⏳ Pending
43 | LMS | Course creation flow rework (Facebook Campaign style — fill details at each level immediately) | 14 May | High | ⏳ Pending
44 | LMS | Module & Lesson inline editing | 14 May | High | ⏳ Pending
45 | LMS | Course Timeline: auto-generate based on start date + lesson/module durations | 14 May | Medium | ⏳ Pending
46 | LMS | Live Sessions improvements | 14 May | Medium | ⏳ Pending
47 | LMS | Discount Vouchers (Instructor Settings) | 14 May | Medium | ⏳ Pending
48 | LMS | People Tab: instructor roles management | 14 May | Medium | ⏳ Pending
49 | LMS | Quizzes & Assessments improvements | 14 May | High | ⏳ Pending
50 | LMS | Assignments improvements | 14 May | High | ⏳ Pending
51 | LMS | LMS Certificates: course completion certificates | 14 May | Medium | ⏳ Pending
Registration / Sign-up (3 items)
52 | Registration / Sign-up | Sign in with Apple ID | 4 May | Medium | ⏳ Pending
53 | Registration / Sign-up | Email verification (OTP) | 4 May | High | ⏳ Pending
54 | Registration / Sign-up | Phone/SMS verification (OTP) — no WhatsApp OTP | 4 May | High | ⏳ Pending
Technical / Backend (12 items)
55 | Technical / Backend | Payment Gateway integration | 4 May | High | ⏳ Pending
56 | Technical / Backend | Email delivery service for verification + prescriptions | 4 May | High | ⏳ Pending
57 | Technical / Backend | SMS service for phone verification | 4 May | High | ⏳ Pending
58 | Technical / Backend | Full multi-language support for all UI elements (English + Urdu) | 4 May | Medium | ⏳ Pending
59 | Technical / Backend | Data encryption | 4 May | High | ⏳ Pending
60 | Technical / Backend | 2FA (Two-Factor Authentication) — optional | 4 May | Low | ⏳ Pending
61 | Technical / Backend | Appointment reminders: 1 hour before + 10 minutes before | 4 May | Medium | ⏳ Pending
62 | Technical / Backend | Order notifications: confirmed, dispatched, delivered | 4 May | High | ⏳ Pending
63 | Technical / Backend | Color scheme: Labs = Orange, Pharmacy = Blue, Conditions = Purple | 4 May | Medium | ⏳ Pending
64 | Technical / Backend | Specialty icons (heart for cardiology, brain for neurology, skin, eye, etc.) | 4 May | Low | ⏳ Pending
65 | Technical / Backend | Multi-select forms and clear validation messages | 4 May | Medium | ⏳ Pending
66 | Technical / Backend | Platform fee: client requested to DELETE this feature | 21 April | High | ⏳ Pending
Admin Panel (3 items)
67 | Admin Panel | Doctor management improvements | 14 May | High | ⏳ Pending
68 | Admin Panel | Content & Community management | 14 May | Medium | ⏳ Pending
69 | Admin Panel | FAQs management system | 14 May | Medium | ⏳ Pending
General / Cross-cutting (8 items)
70 | General / Cross-cutting | Help Center — Message Support Form (all accounts) | 14 May | Medium | ⏳ Pending
71 | General / Cross-cutting | Notification position fix (all accounts) | 14 May | Medium | ⏳ Pending
72 | General / Cross-cutting | Settings improvements (all accounts) | 14 May | Medium | ⏳ Pending
73 | General / Cross-cutting | Phone/WhatsApp contact for all accounts except patient | 14 May | Medium | ⏳ Pending
74 | General / Cross-cutting | Biometric / FaceID login (app-level) | 14 May | Medium | ⏳ Pending
75 | General / Cross-cutting | Health Community improvements | 14 May | Medium | ⏳ Pending
76 | General / Cross-cutting | FAQs section (all accounts) | 14 May | Medium | ⏳ Pending
77 | General / Cross-cutting | iCare Main Domain setup | 14 May | High | ⏳ Pending
Newly Added Tasks (9 items)
78 | Login / Signup | Login page: Signup modal not working — replace with link text to patient signup page | New | Medium | ⏳ Pending
79 | Admin Panel | When logged in as Admin, 'Add Doctor / etc.' button hides behind WhatsApp icon | New | Medium | ⏳ Pending
80 | Admin Panel | Admin approval cards don't show doctor details (qualification, etc.) | New | Medium | ⏳ Pending
81 | Admin Panel | Admin dashboard 'Add New Doctor' not working | New | Medium | ⏳ Pending
82 | Admin Panel | Admin panel 'Verify Doctors' — data not showing | New | Medium | ⏳ Pending
83 | Admin Panel | No option to manage Doctors and other user types | New | Medium | ⏳ Pending
84 | Admin Panel | Users Deactivate option missing | New | Medium | ⏳ Pending
85 | Doctor Account | Doctor Signup: Specialist and Degree dropdown missing | New | Medium | ⏳ Pending
86 | General / Cross-cutting | Website open URL should default to Home page | New | Medium | ⏳ Pending

## 📊 Summary
iCare Virtual Hospital — Project Status Summary
As of June 12, 2026 ¦ Source: Simplified Changes Documents (11 Apr – 14 May 2026)
Total Tasks Identified | 265
✅ Completed | 179
⏳ Pending | 86
Overall Completion % | 67.5%
🔴 High Priority Pending | 29
🟡 Medium Priority Pending | 39
🔵 Low Priority Pending | 9
Per-Module Breakdown
Module | Completed | Pending | Total | % Done
Doctor Account | 25 | 8 | 33 | 76%
Patient Account | 13 | 8 | 21 | 62%
Home Page | 27 | 0 | 27 | 100%
Video Consultation | 5 | 1 | 6 | 83%
Prescription Management | 6 | 0 | 6 | 100%
Health Tracker | 13 | 0 | 13 | 100%
Pharmacy Account | 27 | 6 | 33 | 82%
Laboratory Account | 30 | 11 | 41 | 73%
LMS | 7 | 17 | 24 | 29%
Registration / Sign-up | 9 | 3 | 12 | 75%
General / Cross-cutting | 15 | 8 | 23 | 65%
Technical / Backend | 0 | 12 | 12 | 0%
Admin Panel | 0 | 3 | 3 | 0%